## Summary
Project | Initial Review | Design | Approvals | Bid | Permitting | Construction | Cost | Grant $ | Grant Source | Cost to Mexico Beach | Current Update | Previous Update | Previous Update | Previous Update | Previous Update | Previous Update | Previous Update | Previous Update | Previous Update | Previous Update | Previous Update
Pier | In Process | 10/2025 | TBD | TBD | TBD | TBD | TBD | TBD | FEMA | 0 | 3/31 - No update. | 3/17 - FEMA decided they would allow fish tubes. The plan has been changed back. Bid package has been received, Mexico Beach and AtkinsRealis are currently reviewing. Next step is putting the package out for bidding. | 3/3 - We've had to change the design in our quest for approval; we've removed the fish tubes and replaced them with garbage cans. No other updates. | 2/17 - No substantial update. Waiting for bid package. FEMA required removal of fish waste pipes, proposal updated. | 2/3 - No substantial update. Waiting for bid package. | 1/13 No substantial update. Still waiting on bid package. | 12/23 - We continue to have weekly meetings. We are progressing through some of the required environmental studies while we wait for the bid package. | 11/25 - BDI currently working on bid package per FEMA's request; FEMA needs the bid to determine grant award amount. This does not mean construction will be starting. | 11/25 - BDI currently working on bid package. | 11/10 - Waiting on two biological assessments after which point it will go to the Army Corps of Engineers. BDI working on bid package - bids need to be done so FEMA can properly cost project. FEMA will most likely pay for rebuilding in existing footprint, but not moving it 200' seaward to get into deeper water. | 10/16 - FEMA holding up review. Several fed agencies need to approve; approval slowed down by recent hurricane response, could take up to a year total
15th St. Pedestrian Bridge | Complete | Complete | Complete | Complete | TBD | TBD | 663068 | 350000 | State Appr | 313068 | 3/31 - Special meeting 4/3 to discuss options. | 3/17 - Currently working on options. | 3/3 - Bids came in $300k over expectations. Currently working to find alternative funding sources. | 2/17 - No update, RFP is out, receiving some questions, addendum will be added to answer questions. Bids closed 2/14. | 2/3 - RFP is out, receiving some questions, addendum will be added to answer questions. | 1/13 - Final set of drawings have arrived, currently in internal review at Mexico Beach. RFB will go out by the end of the week. | 12/23 - No update - still waiting on final set of drawings. | 12/9 - FDOT had no comments; Anchor is assembling final set of drawings for the procurement package. It will be posted for bid after that. | 11/25 - Plans sent to FDOT for comments | 11/10 - Anchor responded to FDOT review comments and resubmitted drawings for review | 10/30 - Anchor working on responses to FDOT design review comments
Amphitheater | Complete | Complete | Complete | Complete | TBD | TBD | TBD | 280000 | ARPA | 0 | 3/31 - Bid selected, moving forward. | 3/17 - Bidding closed, will come before next Council meeting for approval. Winning bid came in at $271,000. | 3/3 - Bidding still open. | 2/17 - funds verified, out for bid. | 2/3 - Waiting on funds verification. Grant funds of around $500k were received for several projects; going through bank and financial statements to verify availability. | 1/13 - Draft request for proposals received and ready to go. Currently verifying funds availability. | 12/23 - No update - still have not received procurement or design criteria drafts | 12/9 - Procurement documentation and design criteria drafts will be sent to the City by 12/20 for review. | 11/25 - Was discussed at last council meeting, Anchor is working on plan. | 11/10 - Project will be on the 11/12 council meeting agenda to discuss aesthetics and what City wants | 10/30 - Anchor working on bid docs (RFQ, design criteria) - come before counicl in Nov for ideas
Metal Warehouse (Public Works) | Complete | Complete | In Process | In Process | TBD | TBD | TBD | N/A | N/A | 100000 | 3/31 - Two quotes have been provided for the removal of the water tower foundations, both quotes are approximately $60,000.00. Anchor will hold until the City is ready to proceed with a location. Building itself should be around $200 per square foot. | 3/17 - Partially removing foundations will be $58k. Currently working on potential other locations. | 3/3 - Anchor is looking at other potential locations to avoid a $60k bill for removing the old water tower footings. | 2/17 - one quote received for removing old water tower footings, two additional quotes needed. | 2/3 - Anchor spoke with contractor on 1/20 to obtain quote for removing concrete footings. Location has been approved internally pending their removal. | 1/13 - We confirmed placement will work provided the footings can be removed; waiting on that quote. | 12/23 - New plan sent to us on 12/19. PW, Utilities, and Admin are currently reviewing. | 12/9 - Anchor is coordinating with Rigsby Crane regarding removal of water tower foundation. There are no as-builts. Rigsby will be onsite analyzing whether we can just remove the top 3'-4' instead. | 11/10 - Demolition company is putting together proposal to remove foundations of water tower to free up locations on site for the metal building; will update when we receive their proposal. Anchor is also updating/finalizing Design Criteria Package and RFP and will send those drafts to City staff for review. | 10/30 - Anchor working on foundation plan, Colex Crance coming week of 10/28 to assess current site
Kayak Launch | Complete | Complete | Complete | Complete | Complete | Complete | 80000 | 40000 | FDEP | 40000 | Complete | Complete | Complete | Complete | Complete | Complete | 12/23 - Fully assembled and installed, signage is up. Planning grand opening w/media after the holidays. | 12/9 - Being assembled. Dock is in the water, working on ramp. | 11/25 - Dock ordered, arrival early December | 11/10 - FDEP permitting underway; FDEP requested additional information and Anchor responded to the request, FDEP reviewing | 10/30 - Dock ordered, FDEP reviewing permit exemption application
Boat Ramp Expansion & Repairs | Complete | Complete | Complete | TBD | TBD | TBD | 750000 | 950000 | FWC | 0 | 3/31 - Anchor is updating grant language with estimated quantities while working with CAD draftsman to get 30% design layout and details complete and working on draft technical specifications and draft request for proposals for bidding phase | 3/17 - no update. | 3/3 - no update. | 2/17 - task order approved, work beginning | 2/3 - Task Order and Notice to Proceed will be heard at the first Februrary Council meeting. | 1/13 - Most recent drawings received, will go before council at 2nd Jan meeting. | 12/23 - No update. | 12/9 - Anchor is working on updated proposal for engineering design services to include the revised plan and seawall repair a swell as grant agreement language updates. We'll have this by 12/20. | 11/25 - FWC is reviewing; they need to approve grant funds for the project changes | 11/10 - Project will be on the 11/12 council meeting agenda for discussion; FWC Grant rep will also try to attend | 10/30 - Cost extimate and grant agreement revision complete, new FWC agreement to Council in Nov, FWC rep may attend
Boat Ramp Repairs | Complete | Complete | Complete | TBD | TBD | TBD | TBD | TBD | TBD | 800000 | 3/31 - see above. | 3/17 - see above. | 3/3 - see above. | Funds are 600k Canal/ 200k Boat Launch from Gen Fund | See above. | See above. | 12/23 - No update. | 10/30 - Will be part of expansion project above (repairs to seawall) | 10/30 - Will be part of expansion project above (repairs to seawall)
Water Tank Aeration | Complete | Complete | Complete | In Process | TBD | TBD | TBD | N/A | N/A | 25000 | 3/31 - Anchor is looking into value engineering options to reduce construction costs as well as looking into different vendors and options for aeration systems. | 3/17 - Bid came in at over $250k. Working with Anchor to determine if we need to change the bid package to be more specific or clear. | 3/3 - Bidding still open. | 2/17 - Bid posted. | 2/3 - Bid will be posted by 2/8. | 1/13 - Receiving final bid package by end of the week. Next step is bidding. | 12/23 - Still in review, expect approval 12/30. | 12/9 - Drawings sent to City, in review. Expect approval by 12/20. | 11/10 - Proposed plans for system received, currently in review | 10/30 - Anchor visiting similar system in PSJ, working on drawings and bid docs
Water/Sewer Assessment | In Process | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 3/17 - no update. | 3/17 - no update. | 3/3 - no update. | 2/3 - No update. Still waiting on FDEP. | 2/3 - No update. Still waiting on FDEP. | 1/13 - No update, still waiting on FDEP | 12/23 - No update, still waiting on FDEP | 10/30 - Anchor waiting for FDEP consent order | 10/30 - Anchor waiting for FDEP consent order
MX-1 Relocation | In Process | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Inactive | Inactive | Inactive | 2/17 - Project going incactive. New plan is to seek appropriations for sewage system study to either fix system or justify moving. | 2/3 - No update, still waiting on FDEP. | 1/13 - No update, still waiting on FDEP. Currently looking at alternate funding sources. | 12/23 - No update, still waiting on FDEP | 10/30 - Anchor waiting for FDEP consent order | 10/30 - Anchor waiting for FDEP consent order
Jetty | Complete | Complete | Complete | In Process | TBD | TBD | TBD | 3500000 | FEMA | 0 | 3/17 - out for bid. | 3/17 - out for bid. | 3/3 - bid package received, reviewing prior to putting out for bid. | 2/17 - Creating updated bid package. | 2/3 - Waiting until renourishment is complete in that area before putting out for bid. | 1/13 - Waiting until renourishment is complete in that area before putting out for bid. | 12/23 - Reached out to Dewberry again to get bid package. | 10/16 - Dewberry preparing bid pacakge | 10/16 - Dewberry preparing bid pacakge
Hwy 98 Resurfacing - Moving Utilities | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | TBD | TBD | TBD | TBD | [7 empty] | 12/9 - City Council voted to not include turn lanes; this project will be removed from the list. | 11/25 - cost to move as discussed came in at $450k. Contractor is working on other options. |  | 10/30 - Waiting for price from contractor, Anchor reached out to construction admin team
Hwy 98 Resurfacing - Resurfacing Not Run by Mexico Beach | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/17 - no update. | 3/17 - no update. | 3/3 - lane closures and resurfacing of main travel lanes should begin this week. | 2/17 - Crosswalk reconstruction has begun, still no timeline. | 2/3 - No update. | 1/13 - No update. | 12/23 - FDOT is doing some redesign. Original plan had drainage running down 16th. That is being changed but the actual change has not been decided yet. | 11/25 - Work is beginning. | 11/25 - Work is beginning. | 11/10 - Anchor reached out to the Project Manager who said the project is now in the construction admin phase; Anchor reached out to CA phase contact for coordination – awaiting response
MobiMats (150' In Storage) | By 3/2025 | By 5/2025 | TBD | TBD | TBD | TBD | TBD | N/A | N/A | TBD | 3/31 - No update. Working on layout including new dune at Sunset Park. | 3/17 - survey received, engineers are working on draft layout options. | 3/3 - survey received, engineers are working on draft layout options. | 2/17 - No update. Waiting for new engineering report to determine placement and permitting from FDEP. | 2/3 - Waiting for new engineering report to determine placement and permitting from FDEP. | 1/13 - Waiting for new engineering report to determine placement; will be provided by end of the week. | 12/23 - Working on updated plan, moving from 37th to Sunset Park. | 12/9 - Location changing from 37th to Sunsent Park. Anchor will have new proposals by 12/20 | 11/25 - Drawings updated, working on permits | 11/10 - City staff confirmed how much mat the City has on hand, Anchor updating drawings to show layout options | 10/30 - After dune walkover project designed; need locations for permit
Boat Ramp Lean-To | In Process | By 5/2025 | TBD | TBD | TBD | TBD | TBD | N/A | N/A | 25000 | 3/17 - no update. | 3/17 - no update. | 3/3 - no update. | 2/17 - No update. Must wait until boat ramp design is finalized to determine size and location. | 2/3 - No update. Must wait until boat ramp design is finalized to determine size and location. | 1/13 - Must wait until boat ramp design is finalized to determine size and location. | 12/23 - No update. | 12/9 - Will begin process in January 2025 | 11/25 - No update
Drive-On Boat Dock for BCSO | In Process | By 5/2025 | TBD | TBD | TBD | TBD | TBD | N/A | N/A | 15000 | 3/17 - no update. | 3/17 - no update. | 3/3 - no update. | 2/17 - BCSO will be orderin in the near future. Most funding will come from police impact fees. | 2/3 - No update. BCSO will be orderin in the near future. | 1/13 - BCSO will be orderin in the near future. | 12/23 - Just a purchase, not a full project. BCSO is handling. | 12/9 - Will begin process in January 2025 | 11/25 - No udpate
Police/Fire Station | In Process | TBD | TBD | TBD | TBD | TBD | 10000000 | 4000000 | FEMA | 0 | 3/17 - State approved appeal, now sent to FEMA. | 3/17 - State approved appeal, now sent to FEMA. | 3/3 - State approved appeal, now sent to FEMA. | 2/17 - No update. Appeal has been submitted. It is currently working through the appeal process which could take 60 days. | 2/3 - Appeal has been submitted. It is currently working through the appeal process which could take 60 days. | 1/13 - Scheduling meeting with FDEM first week of Feb to discuss appeal prior to their submission to FEMA. | 12/23 - Appeal package received from AtkinsRealis and signed by Administrator. Will be submitted to FEMA. | 12/9 - AtkinsRealis is working on appeal package. | 11/10 - FEMA denied $6mm of our $10mm request, determining that the facility should be built in the existing footprint. We are appealing. | 11/10 - FEMA denied $6mm of our $10mm request, determining that the facility should be built in the existing footprint. We are appealing. | 10/16 - FEMA holding up review. Several fed agencies need to approve; approval slowed down by recent hurricane response.
Restrooms - Parker Park, UTP Park | Complete | Complete | Complete | Complete | Complete | By 2/2025 | 280000 | N/A | N/A | 280000 | 3/17 - builidngs delivered, power and water hooked up, concrete pads poured. Opening 3/21. | 3/17 - builidngs delivered, power and water hooked up, concrete pads poured. Opening 3/21. | 3/3 - builidngs delivered, power and water hookup this week. | 2/17 - No update. Manufacturing delays pushed delivery and install back to March. | 2/3 - Manufacturing delays pushed delivery and install back to March. | 1/13 - All prep work complete, will be installed by 1/31. | 12/23 - Base delivered, plumbing run, waiting on delivery of restrooms | 11/25 - concrete pad at Parker dug up, waiting on base to be delivered | 11/25 - concrete pad at Parker dug up, waiting on base to be delivered | 10/16 - Need to run power/sewer and put in concrete pad
Atmospheric Valve Replacement | Complete | Complete | Complete | Complete | Complete | Complete | Complete | N/A | N/A | 25000 | Complete | Complete | Complete | 2/17 - Completed 12/13/24 | 2/3 - No update. | 1/13 - No update. | 12/23 - No update. | 11/25 - No update | 11/25 - No update
Dune Walkovers | In Process | TBD | TBD | TBD | TBD | TBD | 120000 | 60000 | Coastal Alliance | 60000 | 3/17 -no update until award determination this summer. | 3/17 -no update until award determination this summer. | 3/3 - ranked #2 in grant results, expecting (but not guaranteed), funds. Will find out this summer. | 2/17 - No update. In limbo pending beach renourishment. | 2/3 - No update. In limbo pending beach renourishment. | 1/13 - No update. In limbo pending beach renourishment. | 12/23 - No update. | 10/30 - Grant application submitted 10/29 | 10/30 - Grant application submitted 10/29
14th St. Lift Station Rehab | In Process | Complete | Complete | Complete | In Process | TBD | 800000 | N/A | N/A | 800000 | 3/31 - no update. Coming before council in April. | 3/17 - funding verified. Will come before Council for approval. | 3/3 - looking at alternatives to full rehab. | 2/17 - Mexico Beach is reviewing proposal from Anchor | 2/3 - No update. Anchor still reviewing. | 1/13 - No update. Anchor still reviewing. | 12/23 - No update. Anchor still reviewing. | 12/9 - We've learned the bid process was completed on 10/10/23. Low bidder has agreed to honor their price from a year ago. We are reevaluating the construction plan and permits to ensure nothing has changed over the last year. Work should begin after the new year.
Nanook Lift Station Rehab | In Process | Complete | Complete | Complete | In Process | TBD | 425000 | N/A | N/A | 425000 | 3/31 - no update. Coming before council in April. | 3/17 - funding verified. Will come before Council for approval. | 3/3 - looking at alternatives to full rehab. | 2/17 - Mexico Beach is reviewing proposal from Anchor | 2/3 - No update. Anchor still reviewing. | 1/13 - No update. Anchor still reviewing. | 12/23 - No update. Anchor still reviewing. | 12/9 - We've learned the bid process was completed on 10/10/23. Low bidder has agreed to honor their price from a year ago. We are reevaluating the construction plan and permits to ensure nothing has changed over the last year. Work should begin after the new year.
Comp Plan/LDR Revision | In Process | [5 empty] | TBD | N/A | N/A | 50000 | 3/17 - First set of items given to P&Z for their recommendations. | 3/17 - First set of items given to P&Z for their recommendations. | 3/3 - First set of items given to P&Z for their recommendations. | 2/17 - List of suggested first steps will be presented at 2/25 Council meeting for review. | 2/3 - List of suggested first steps will be presented at 2/11 Council meeting for review. | 1/13 - 2nd workshop held, next steps being decided 1/14. | 12/23 - Next workshop is 1/8 at 9am | 12/9 - Two workshops scheduled 12/16 6pm and 1/8 9am for public input. | 11/25 - several meetings scheduled, will be discussed at 11/26 Council meeting | 10/16 - Figuring out scope for this fiscal year
Stormwater Plan | Complete | In Process | TBD | TBD | TBD | TBD | TBD | 7000000 | FEMA | TBD | 3/17 - no update. On the 3/25 council agenda. | 3/17 - no update. On the 3/25 council agenda. | 3/3 - no update. | 2/17 - Results will be presented to the Council 3/18/25 | 2/3 - No update. Reached out to contractor to check in. | 1/13 - No update. | 12/23 - AVCON still working. We do have a solution for 4th from AVCON; working on costing it out to determine next steps. | 12/9 - AVCON is working on overall plan after having on-site meetings and physical evaluation. |  | 11/10 - Two of eight problem sites visited; AVCON is working on potential solutions | 10/30 - AVCON preparing plan, visiting problem sites 11/5/24
Bypass Pump Platforms & Installation | Complete | Complete | Complete | In Process | TBD | TBD | 781000 | 453000 | FEMA | 328000 | 3/31 - no update. | 3/17 - three separate proposals came in. Working with Atkins Realis to submit to FEMA, will need to find ways to fund the other two internally. | 3/3 - waiting on three proposals. | 2/17 - No update. | 2/3 - Bid came back over budget, Council declined. Admninistrator is reaching out to contrators to possibly change scope to decrease cost. | 1/13 - Bid came back over budget. Working with legal on next steps for possibly splitting work between contractor and in-house. | 12/23 - Bids opened, bidder selected, waiting for financial feasability determination/Grant funds availability from AtkinsRealis. | 11/25 - Put out for bid | 11/25 - Put out for bid
Salt Creek 2 Not Run by Mexico Beach | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/31 - no update. | 3/17 - no update. | 3/3 - no update. | 2/17 - No update. Commercial lot work has begun. | 2/3 - No update. Commercial lot work has begun. | 1/13 - Commercial lot work has begun. | 12/23 - No update. | 10/30 - We asked Anchor to review water permits - currently in process | 10/30 - We asked Anchor to review water permits - currently in process
Hwy 98 and 15th St. Multi-Use Path Not Run by Mexico Beach | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3/31 - no update. | 3/17 - no update. | 3/3 - no update. |  |  | 1/13 - No update. | 12/23 - No update. | 12/9 - FDOT responded to our questions. Answers posted on website. | 11/10 - Anchor also reached out to FDOT re: the study to add a multi-use path along 15th Street and it’s proposed location on the south side of the vehicular bridge. The FDOT Project Manager said they could propose the multi-use path be on the north side of the bridge to utilize the proposed pedestrian bridge. Anchor will continue to coordinate with FDOT on this. | 10/30 - This is an FDOT project; we have no control. On this list for information purposes only.